## Planilha1
Data	Hora inicio	Hora fim	Descrição
09/03/2022	14:00:00	14:30:00	Criação do projeto laravel e conexão com postgres	00:29:59		188,283888888889
14/03/2022	15:45:00	16:10:00	Casos de uso e começo do diagrama ER	00:25:00
14/03/2022	16:20:00	17:30:00	Parte do diagrama ER e revisão geral do projeto	01:09:59
20/03/2022	15:19:59	15:30:00	Estudo da Integração PHP mercado pago	00:10:01
20/03/2022	16:25:00	17:20:00	Estudo da Integração PHP mercado pago	00:54:57
20/03/2022	17:40:00	18:50:00	Estudo da Integração PHP mercado pago	01:09:59
21/03/2022	10:55:00	13:30:00	Mudança de planos: Pagamento não será redirecionado, falha ao gerar boleto	02:35:00
21/03/2022	15:30:00	19:40:00	Request, Model, Migration, Seeder, API Route and Factory for User	04:09:59
22/03/2022	15:00:00	18:15:00	Finalizado CRUD User	03:14:59
23/03/2022	13:55:00	15:50:00	Início da autenticação	01:54:59
23/03/2022	19:20:00	20:25:00	Autenticação e envio de e-mail	01:04:59
24/03/2022	16:49:59	18:10:00	Redefinição de senhas	01:20:00
25/03/2022	15:30:00	18:00:00	Verificação de e-mail, refatoração e vue.js	02:29:59
31/03/2022	14:10:00	15:19:59	Estilizando Landing Page	01:09:58
10/04/2022	17:10:00	19:50:00	Estilizando Landing Page	02:39:59
11/04/2022	20:20:00	21:55:00	Estilizando Landing Page	01:34:59
13/04/2022	11:00:00	11:45:00	Estilizando Landing Page	00:45:00
14/04/2022	10:25:00	13:55:00	Landing Page concluída	03:30:00
15/04/2022	11:40:00	14:10:00	Estilizando Formulário de login	02:30:00
16/04/2022	11:00:00	12:08:00	Estilizando Formulário de registro	01:08:00
16/04/2022	12:30:00	14:40:00	Estilizando Formulário de registro	02:10:00
16/04/2022	16:00:00	17:00:00	Editando Controller de registro	01:00:00
17/04/2022	14:45:00	15:40:00	Form de verificação de e-mails e limpando blade APP	00:54:57
17/04/2022	16:00:00	17:20:00	Configure Vue3 and vue-router	01:20:00
17/04/2022	20:15:00	23:50:00	Style header, footer and main content	03:35:00
18/04/2022	14:30:00	16:40:00	Img minify and frontend routes	02:10:00
19/04/2022	13:45:00	17:15:00	Frontend Components and Home page	03:30:00
19/04/2022	19:50:00	21:50:00	Solve client routing	02:00:00
20/04/2022	17:10:00	18:10:00	Acompanhamento do projeto e testes iniciais	00:59:59
21/04/2022	13:30:00	14:00:00	Material Icons import	00:30:00
21/04/2022	16:20:00	18:50:00	Admin pages and some components	02:29:59
23/04/2022	18:45:00	22:10:00	Inputs and form data	03:25:00
24/04/2022	18:35:00	19:50:00	Admin: tournaments and users pages, client: tournaments and home page	01:14:59
25/04/2022	18:00:00	21:40:00	Client frontend further styling and useful components, v-model correction	03:40:00
26/04/2022	19:20:00	21:40:00	Client profile page	02:19:59
27/04/2022	18:45:00	21:00:00	Admin modals and register components	02:15:00
27/04/2022	21:30:00	22:40:00	Better structure and admin pages	01:09:59
28/04/2022	19:20:00	19:30:00	Admin Pages and better file structuring	00:09:59
28/04/2022	19:50:00	20:25:00	Admin Pages and better file structuring	00:35:00
28/04/2022	20:40:00	23:30:00	Admin Pages and better file structuring	02:49:59
29/04/2022	14:05:00	15:19:59	Admin settings page	01:14:58
29/04/2022	16:49:59	17:50:00	Backend stuff	01:00:00
01/05/2022	17:40:00	19:40:00	Tournaments migrations, ER and requests	01:59:59
01/05/2022	22:14:00	23:59:00	API auth, tournament controller	01:44:59
02/05/2022	18:49:00	23:59:00	Recurring tournaments controller and auth fixes	05:10:00
03/05/2022	18:15:00	19:30:00	Create tournament modal	01:15:00
03/05/2022	21:00:00	21:20:00	Hostgator credentials and SSH failure	00:19:59
03/05/2022	21:20:00	23:00:00	User and tournaments dynamic data, Model adjustments	01:40:00
04/05/2022	00:30:00	01:35:00	Dynamic prices landing page and some api resources	01:05:00
04/05/2022	18:10:00	20:55:00	Global data and update plan prices	02:45:00
04/05/2022	21:00:00	21:30:00	Dynamic users using store	00:30:00
06/05/2022	00:30:00	01:30:00	CRUD de notificações	01:00:00
06/05/2022	21:05:00	23:59:00	Payment CRUD, EULA upload and Register user modal	02:54:00
07/05/2022	10:10:00	10:45:00	notification intervals	00:35:00
07/05/2022	10:55:00	12:40:00	CRUD notifications Frontend	01:45:00
07/05/2022	12:40:00	14:40:00	Ad backend	02:00:00
07/05/2022	15:46:00	17:40:00	Ads CUD	01:54:00
08/05/2022	16:40:00	18:40:00	Finish Ads CRUD	02:00:00
08/05/2022	20:50:00	22:20:00	Register Stepper	01:30:00
08/05/2022	22:15:00	23:59:00	Tournament Plataforms and types	01:43:59
09/05/2022	01:50:00	02:40:00	Configuring php, composer, laravel and htaccess for production	00:49:59
09/05/2022	19:30:00	22:45:00	Cadastro e aprovação de torneios (com recorrência)	03:14:59
10/05/2022	00:00:00	02:00:00	Edição de Torneios e Insights (back e front)	02:00:00
10/05/2022	03:00:00	04:05:00	Filtros de torneio e usuário	01:05:00
10/05/2022	11:55:00	12:45:00	Filtros restantes de admin	00:49:59
10/05/2022	12:45:00	13:25:00	Início da publicação admin	00:40:00
10/05/2022	18:42:00	19:20:00	Publicação admin	00:38:00
11/05/2022	16:55:00	18:10:00	Testes iniciais admin	01:14:59
13/05/2022	01:15:00	01:54:59	Favicon and password reset and update pages	00:39:59
13/05/2022	01:54:59	02:15:00	Página de torneios client integrada	00:20:01
13/05/2022	02:20:00	04:05:00	Fixed timeInput	01:45:00
13/05/2022	04:05:00	04:40:00	Fixed htaccess redirects	00:34:59
20/05/2022	20:50:00	22:50:00	Show notifications from user backend	01:59:59
21/05/2022	18:19:59	19:20:00	Notifications fetch frontend	01:00:00
21/05/2022	19:40:00	21:35:00	Enable regular notification modal	01:54:59
22/05/2022	17:50:00	18:30:00	Enable regular notification integration	00:40:00
22/05/2022	18:40:00	19:20:00	Install serviceworker	00:40:00
23/05/2022	17:00:00	18:00:00	Notificações sendo exibidas, a princípio	00:59:59
23/05/2022	18:40:00	22:20:00	Notificações sendo exibidas, a princípio	03:40:00
25/05/2022	15:40:00	17:20:00	Instalando ambiente no notebook	01:39:59
25/05/2022	17:20:00	18:19:59	Disable notifications back e front	00:59:59
25/05/2022	19:20:00	22:00:00	Setup new environment	02:39:59
27/05/2022	20:30:00	22:10:00	Visão geral dos protocolos do mercadopago	01:40:00
30/05/2022	15:19:59	17:20:00	Leitura e testes com API mercadopago	02:00:01
30/05/2022	18:50:00	20:05:00	Exemplo mercadopago frontend and fix bugs	01:15:00
30/05/2022	20:50:00	21:40:00	Arrumando ambiente de integração	00:49:59
30/05/2022	21:40:00	23:30:00	Mentoria e card token enviado	01:49:59
03/06/2022	11:35:00	12:10:00	Alterar dados do usuário (front)	00:34:59
03/06/2022	13:49:59	14:50:00	Exibir ícones de notificação	01:00:00
03/06/2022	15:50:00	17:50:00	Change payment_method	02:00:00
03/06/2022	21:20:00	23:35:00	Testes e correções de bug	02:15:00
04/06/2022	14:30:00	16:40:00	Bug fixes, Load ads, View user page	02:10:00
04/06/2022	17:50:00	18:15:00	Translate pt-BR and fix timezone	00:24:59
04/06/2022	21:00:00	21:55:00	Finished view user page	00:54:57
5-jun	18:30:00	20:00:00	Recorrência quinzenal ajustada	01:30:00
6-jun	15:30:00	17:00:00	Arrumando timeinput	01:30:00
06-jun	17:25:00	17:50:00	Ver torneio	00:25:00
06-jun	20:20:00	20:35:00	Update produção	00:14:59
12-jun	12:00:00	13:15:00	Payment Middleware, change payment and user fields and methods, general adjustments	01:15:00
12-jun	13:55:00	16:40:00	Finish payment controller and not allow user to access platform if not regular	02:44:59
13-jun	23:00:00	23:20:00	Payment Middleware, change payment and user fields and methods, general adjustments	00:19:59
16-jun	01:30:00	03:35:00	MercadoPago Webhooks	02:05:00
16-jun	13:10:00	14:20:00	MercadoPago Webhooks	01:09:59
17-jun	01:00:00	01:30:00	MercadoPago Webhooks	00:30:00
17-jun	15:19:59	18:19:59	MercadoPago tickets and payment controller	03:00:00
20-jun	20:25:00	22:40:00	Reunião de testes	02:15:00
21-jun	00:00:00	01:10:00	User Block improvements	01:10:00
21-jun	01:10:00	01:20:00	Seed Platforms	00:09:59
21-jun	01:20:00	02:00:00	Update produção	00:40:00
24-jun	13:55:00	17:40:00	Fix bugs	03:45:00
25-jun	21:10:00	21:40:00	Prune models and remove ticket when paying with credit card	00:30:00
25-jun	21:40:00	23:20:00	Finalizado Webhook mercadopago	01:39:59
26-jun	12:00:00	18:05:00	Várias melhorias e testes de pagamento, e outras correções solicitadas	06:05:00
05/07/22	15:50:00	16:40:00	Mudando Template de e-mail	00:49:59
07/07/2022	20:05:00	23:55:00	Diversas correções de bug	03:49:59
9-jul	12:19:59	13:00:00	Update produção	00:40:00
13-jul	15:00:00	16:40:00	Botão WhatsApp e removido notification intervals	01:39:59
13-jul	19:30:00	21:00:00	Correções solicitadas pelo cliente, bug fixes e update produção	01:30:00
27-jul	22:30:00	23:00:00	Sincronizando repositórios e novo ambiente de desenvolvimento	00:30:00
27-jul	08:30:00	10:10:00	Ajustes solicitados pelo cliente	01:39:59
27-jul	11:30:00	14:50:00	Ajustes solicitados pelo cliente	03:20:00
8-ago	15:40:00	17:00:00	Ajustes solicitados pelo cliente	01:20:00
08-ago	19:10:00	19:55:00	Ajustes solicitados pelo cliente	00:45:00
10-ago	16:15:00	16:40:00	Alteração do buy-in para float	00:24:59
17-ago	21:20:00	23:40:00	Ajustes solicitados pelo cliente	02:20:00
19/08/22	15:30:00			08:30:00
				00:00:00
				00:00:00
				00:00:00
				00:00:00
				00:00:00
				00:00:00