## Planilha1
Data	Hora inicio	Hora fim	Descrição	Tempo gasto
2022-03-09	PT14H00M00S	PT14H30M00S	Criação do projeto laravel e conexão com postgres	PT00H30M00S		167.54638888888888
2022-03-14	PT15H45M00S	PT16H10M00S	Casos de uso e começo do diagrama ER	PT00H25M00S
2022-03-14	PT16H20M00S	PT17H30M00S	Parte do diagrama ER e revisão geral do projeto	PT01H10M00S
2022-03-20	PT15H19M59S	PT15H30M00S	Estudo da Integração PHP mercado pago	PT00H10M00S
2022-03-20	PT16H25M00S	PT17H20M00S	Estudo da Integração PHP mercado pago	PT00H55M00S
2022-03-20	PT17H40M00S	PT18H50M00S	Estudo da Integração PHP mercado pago	PT01H10M00S
2022-03-21	PT10H55M00S	PT13H30M00S	Mudança de planos: Pagamento não será redirecionado, falha ao gerar boleto	PT02H35M00S
2022-03-21	PT15H30M00S	PT19H40M00S	Request, Model, Migration, Seeder, API Route and Factory for User	PT04H10M00S
2022-03-22	PT15H00M00S	PT18H15M00S	Finalizado CRUD User	PT03H15M00S
2022-03-23	PT13H55M00S	PT15H50M00S	Início da autenticação	PT01H54M59S
2022-03-23	PT19H20M00S	PT20H25M00S	Autenticação e envio de e-mail	PT01H05M00S
2022-03-24	PT16H49M59S	PT18H10M00S	Redefinição de senhas	PT01H20M00S
2022-03-25	PT15H30M00S	PT18H00M00S	Verificação de e-mail, refatoração e vue.js	PT02H30M00S
2022-03-31	PT14H10M00S	PT15H19M59S	Estilizando Landing Page	PT01H10M00S
2022-04-10	PT17H10M00S	PT19H50M00S	Estilizando Landing Page	PT02H40M00S
2022-04-11	PT20H20M00S	PT21H55M00S	Estilizando Landing Page	PT01H35M00S
2022-04-13	PT11H00M00S	PT11H45M00S	Estilizando Landing Page	PT00H45M00S
2022-04-14	PT10H25M00S	PT13H55M00S	Landing Page concluída	PT03H30M00S
2022-04-15	PT11H40M00S	PT14H10M00S	Estilizando Formulário de login	PT02H30M00S
2022-04-16	PT11H00M00S	PT12H08M00S	Estilizando Formulário de registro	PT01H08M00S
2022-04-16	PT12H30M00S	PT14H40M00S	Estilizando Formulário de registro	PT02H10M00S
2022-04-16	PT16H00M00S	PT17H00M00S	Editando Controller de registro	PT01H00M00S
2022-04-17	PT14H45M00S	PT15H40M00S	Form de verificação de e-mails e limpando blade APP	PT00H55M00S
2022-04-17	PT16H00M00S	PT17H20M00S	Configure Vue3 and vue-router	PT01H20M00S
2022-04-17	PT20H15M00S	PT23H50M00S	Style header, footer and main content	PT03H35M00S
2022-04-18	PT14H30M00S	PT16H40M00S	Img minify and frontend routes	PT02H10M00S
2022-04-19	PT13H45M00S	PT17H15M00S	Frontend Components and Home page	PT03H30M00S
2022-04-19	PT19H50M00S	PT21H50M00S	Solve client routing	PT02H00M00S
2022-04-20	PT17H10M00S	PT18H10M00S	Acompanhamento do projeto e testes iniciais	PT01H00M00S
2022-04-21	PT13H30M00S	PT14H00M00S	Material Icons import	PT00H30M00S
2022-04-21	PT16H20M00S	PT18H50M00S	Admin pages and some components	PT02H30M00S
2022-04-23	PT18H45M00S	PT22H10M00S	Inputs and form data	PT03H25M00S
2022-04-24	PT18H35M00S	PT19H50M00S	Admin: tournaments and users pages, client: tournaments and home page	PT01H15M00S
2022-04-25	PT18H00M00S	PT21H40M00S	Client frontend further styling and useful components, v-model correction	PT03H40M00S
2022-04-26	PT19H20M00S	PT21H40M00S	Client profile page	PT02H20M00S
2022-04-27	PT18H45M00S	PT21H00M00S	Admin modals and register components	PT02H15M00S
2022-04-27	PT21H30M00S	PT22H40M00S	Better structure and admin pages	PT01H10M00S
2022-04-28	PT19H20M00S	PT19H30M00S	Admin Pages and better file structuring	PT00H10M00S
2022-04-28	PT19H50M00S	PT20H25M00S	Admin Pages and better file structuring	PT00H35M00S
2022-04-28	PT20H40M00S	PT23H30M00S	Admin Pages and better file structuring	PT02H50M00S
2022-04-29	PT14H05M00S	PT15H19M59S	Admin settings page	PT01H15M00S
2022-04-29	PT16H49M59S	PT17H50M00S	Backend stuff	PT01H00M00S
2022-05-01	PT17H40M00S	PT19H40M00S	Tournaments migrations, ER and requests	PT02H00M00S
2022-05-01	PT22H14M00S	PT23H59M00S	API auth, tournament controller	PT01H45M00S
2022-05-02	PT18H49M00S	PT23H59M00S	Recurring tournaments controller and auth fixes	PT05H10M00S
2022-05-03	PT18H15M00S	PT19H30M00S	Create tournament modal	PT01H15M00S
2022-05-03	PT21H00M00S	PT21H20M00S	Hostgator credentials and SSH failure	PT00H20M00S
2022-05-03	PT21H20M00S	PT23H00M00S	User and tournaments dynamic data, Model adjustments	PT01H40M00S
2022-05-04	PT00H30M00S	PT01H35M00S	Dynamic prices landing page and some api resources	PT01H05M00S
2022-05-04	PT18H10M00S	PT20H55M00S	Global data and update plan prices	PT02H45M00S
2022-05-04	PT21H00M00S	PT21H30M00S	Dynamic users using store	PT00H30M00S
2022-05-06	PT00H30M00S	PT01H30M00S	CRUD de notificações	PT01H00M00S
2022-05-06	PT21H05M00S	PT23H59M00S	Payment CRUD, EULA upload and Register user modal	PT02H54M00S
2022-05-07	PT10H10M00S	PT10H45M00S	notification intervals	PT00H35M00S
2022-05-07	PT10H55M00S	PT12H40M00S	CRUD notifications Frontend	PT01H45M00S
2022-05-07	PT12H40M00S	PT14H40M00S	Ad backend	PT02H00M00S
2022-05-07	PT15H46M00S	PT17H40M00S	Ads CUD	PT01H54M00S
2022-05-08	PT16H40M00S	PT18H40M00S	Finish Ads CRUD	PT02H00M00S
2022-05-08	PT20H50M00S	PT22H20M00S	Register Stepper	PT01H30M00S
2022-05-08	PT22H15M00S	PT23H59M00S	Tournament Plataforms and types	PT01H43M59S
2022-05-09	PT01H50M00S	PT02H40M00S	Configuring php, composer, laravel and htaccess for production	PT00H50M00S
2022-05-09	PT19H30M00S	PT22H45M00S	Cadastro e aprovação de torneios (com recorrência)	PT03H15M00S
2022-05-10	PT00H00M00S	PT02H00M00S	Edição de Torneios e Insights (back e front)	PT02H00M00S
2022-05-10	PT03H00M00S	PT04H05M00S	Filtros de torneio e usuário	PT01H05M00S
2022-05-10	PT11H55M00S	PT12H45M00S	Filtros restantes de admin	PT00H50M00S
2022-05-10	PT12H45M00S	PT13H25M00S	Início da publicação admin	PT00H40M00S
2022-05-10	PT18H42M00S	PT19H20M00S	Publicação admin	PT00H38M00S
2022-05-11	PT16H55M00S	PT18H10M00S	Testes iniciais admin	PT01H15M00S
2022-05-13	PT01H15M00S	PT01H54M59S	Favicon and password reset and update pages	PT00H40M00S
2022-05-13	PT01H54M59S	PT02H15M00S	Página de torneios client integrada	PT00H20M00S
2022-05-13	PT02H20M00S	PT04H05M00S	Fixed timeInput	PT01H45M00S
2022-05-13	PT04H05M00S	PT04H40M00S	Fixed htaccess redirects	PT00H35M00S
2022-05-20	PT20H50M00S	PT22H50M00S	Show notifications from user backend	PT02H00M00S
2022-05-21	PT18H19M59S	PT19H20M00S	Notifications fetch frontend	PT01H00M00S
2022-05-21	PT19H40M00S	PT21H35M00S	Enable regular notification modal	PT01H54M59S
2022-05-22	PT17H50M00S	PT18H30M00S	Enable regular notification integration	PT00H40M00S
2022-05-22	PT18H40M00S	PT19H20M00S	Install serviceworker	PT00H40M00S
2022-05-23	PT17H00M00S	PT18H00M00S	Notificações sendo exibidas, a princípio	PT01H00M00S
2022-05-23	PT18H40M00S	PT22H20M00S	Notificações sendo exibidas, a princípio	PT03H40M00S
2022-05-25	PT15H40M00S	PT17H20M00S	Instalando ambiente no notebook	PT01H40M00S
2022-05-25	PT17H20M00S	PT18H19M59S	Disable notifications back e front	PT01H00M00S
2022-05-25	PT19H20M00S	PT22H00M00S	Setup new environment	PT02H39M59S
2022-05-27	PT20H30M00S	PT22H10M00S	Visão geral dos protocolos do mercadopago	PT01H40M00S
2022-05-30	PT15H19M59S	PT17H20M00S	Leitura e testes com API mercadopago	PT02H00M00S
2022-05-30	PT18H50M00S	PT20H05M00S	Exemplo mercadopago frontend and fix bugs	PT01H15M00S
2022-05-30	PT20H50M00S	PT21H40M00S	Arrumando ambiente de integração	PT00H50M00S
2022-05-30	PT21H40M00S	PT23H30M00S	Mentoria e card token enviado	PT01H50M00S
2022-06-03	PT11H35M00S	PT12H10M00S	Alterar dados do usuário (front)	PT00H34M59S
2022-06-03	PT13H49M59S	PT14H50M00S	Exibir ícones de notificação	PT01H00M00S
2022-06-03	PT15H50M00S	PT17H50M00S	Change payment_method	PT02H00M00S
2022-06-03	PT21H20M00S	PT23H35M00S	Testes e correções de bug	PT02H15M00S
2022-06-04	PT14H30M00S	PT16H40M00S	Bug fixes, Load ads, View user page	PT02H10M00S
2022-06-04	PT17H50M00S	PT18H15M00S	Translate pt-BR and fix timezone	PT00H24M59S
2022-06-04	PT21H00M00S	PT21H55M00S	Finished view user page	PT00H54M57S
2022-06-05	PT18H30M00S	PT20H00M00S	Recorrência quinzenal ajustada	PT01H30M00S
2022-06-06	PT15H30M00S	PT17H00M00S	Arrumando timeinput	PT01H30M00S
2022-06-06	PT17H25M00S	PT17H50M00S	Ver torneio	PT00H25M00S
2022-06-06	PT20H20M00S	PT20H35M00S	Update produção	PT00H14M59S
2022-06-12	PT12H00M00S	PT13H15M00S	Payment Middleware, change payment and user fields and methods, general adjustments	PT01H15M00S
2022-06-12	PT13H55M00S	PT16H40M00S	Finish payment controller and not allow user to access platform if not regular	PT02H44M59S
2022-06-13	PT23H00M00S	PT23H20M00S	Payment Middleware, change payment and user fields and methods, general adjustments	PT00H19M59S
2022-06-16	PT01H30M00S	PT03H35M00S	MercadoPago Webhooks	PT02H05M00S
2022-06-16	PT13H10M00S	PT14H20M00S	MercadoPago Webhooks	PT01H09M59S
2022-06-17	PT01H00M00S	PT01H30M00S	MercadoPago Webhooks	PT00H30M00S
2022-06-17	PT15H19M59S	PT17H10M00S	MercadoPago tickets and payment controller	PT01H50M00S
				PT00H00M00S
				PT00H00M00S